## RP1
Stage | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Contact procedures not initiated | 110 | 109 | 101 | 99 | 99 | 99 | 99 | 96 | 96 | 96 | 82 | 74 | 73 | 57 | 58 | 58
1st or 2nd invites | 21 | 17 | 22 | 20 | 13 | 6 | 4 | 3 | 3 | 1 | 13 | 19 | 15 | 22 | 16 | 12
3rd or more invites | 29 | 34 | 29 | 28 | 29 | 34 | 24 | 18 | 15 | 15 | 15 | 17 | 18 | 19 | 23 | 25
Data sharing discussions and eligibility check | 43 | 38 | 41 | 41 | 42 | 40 | 47 | 45 | 44 | 45 | 36 | 34 | 35 | 43 | 36 | 38
DTA in progress | 19 | 21 | 24 | 19 | 19 | 19 | 24 | 21 | 24 | 26 | 26 | 26 | 28 | 24 | 30 | 25
DTA completed |  | 1 | 1 | 6 | 9 | 9 | 6 | 7 | 7 | 5 | 6 | 5 | 5 | 4 | 1 | 1
Data sets in hand |  |  |  | 4 | 4 | 6 | 7 | 12 | 13 | 15 | 16 | 18 | 19 | 22 | 25 | 28
Ineligible/declined participation/data currently unavailable |  | 2 | 4 | 5 | 7 | 9 | 11 | 20 | 21 | 21 | 30 | 31 | 31 | 33 | 34 | 36

## Abj_outputs
Stage | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Contact procedures not initiated | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ineligible/declined participation/data currently unavailable | Jan: 3; Feb: 3; Mar: 3; Apr: 0
1st or 2nd invites | 6 | 6 | 6 | 4 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3rd or more invite | 7 | 5 | 5 | 5 | 6 | 7 | 7 | 7 | 7 | 2 | 2 | 2 | 2
Data sharing discussions and eligibility check | 0 | 4 | 4 | 11 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0
DTA in progress |  |  |  |  | 4 | 4 | 4 | 4 | 4 | 14 | 12 | 12 | 15
DTA completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2
Data sets in hand | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Jhb_outputs
Stage | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Contact procedures not initiated | 32 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ineligible/declined participation/data currently unavailable |  |  |  | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
1st or 2nd invites | 2 | 1 | 12 | 8 | 6 | 6 | 4 | 2 | 2 | 2 | 2 | 2 | 2
3rd or more invite | 1 |  | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 2 | 2 | 2 | 2
Data sharing discussions and eligibility check | 8 | 37 | 21 | 19 | 17 | 17 | 20 | 14 | 14 | 15 | 15 | 15 | 15
DTA in progress | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 12 | 10 | 10 | 9 | 3 | 3
DTA completed | Dec: 2; Jan: 2; Feb: 2; Mar: 8; Apr: 2
Datasets in-hand | 0 | 3 | 6 | 6 | 7 | 7 | 8 | 9 | 9 | 7 | 8 | 8 | 14

## RP1_Countries
Study site | 1st invite | 2nd invite | 3rd or more invite | Interested | Follow up on interest | Study documents received | Eligibility confirmed | Entering DTA | DTA complete | Ineligible | Declined participation | Data unavailable
Benin | 1 |  | 1 | [7 empty] | 1
Burkina Faso |  |  | 3 | [6 empty] | 1
Cameroon |  |  | 1 |  | 1
Côte d'Ivoire |  |  |  |  | 1
Ethiopia |  |  | 8 |  | 5 | 1 |  | 3 | 1
Gambia |  | 1
Ghana |  | 1 | 3 | 2 | 1 |  |  | 2 |  | 1
Kenya |  |  |  | 2 |  |  |  | 6 | 2 | 1 | 6
Malawi |  |  |  | 1 |  |  | 1 | 2 | 12 | 2 | 1
Nigeria
Senegal |  |  | 1
South Africa | 1 |  | 2 | 2 | 2 |  | 4 | 5 | 11 | 2 | 2 | 1
Tanzania |  |  | 3 | 4 |  |  |  | 5 | 1 | 2 | 8
Multi-country | 4 | 1 | 3 | 3 | 4 |  | 1 | 1 | 4 | 3 | 1